## Slide 1: NRB PROJECTS Y2025 Dilruba Yasmin January 18, 2025

## Slide 2: PROJECT 1: GREEN BD CLEAN BD
OBJECTIVE
Make Bangladesh
greener and cleaner
through sustainable practices
Address the current environmental challenges and the impacts on health, economy, and quality of life
Build a connection between local community and NRBs
IMPLEMENTATION PLAN
Phase1:
Small-scale/Pilot program Launch
Community involvement for tree plantation,
clean-up campaigns, awareness etc.
Phase2:
  Multiple the pilot
with lesson learn in different location
CHALLENGES & MITIGATION
Challenges:
Funding (donations, grants, partnerships)
Continuation and Maintenance
Mitigations:
Stakeholder
Engagement
Communication/Transpa rency/Reporting

## Slide 3: PROJECT 1: GREEN BD CLEAN BD - Implementation and Budget Framework
Community Engagement and Awareness
Sapling Purchase
Planting and Maintenance
Monitoring and Reporting
Contingency Plan

## Slide 4: PROJECT 2: EMPOWER-U/ FUTURE READY/SKILL UP
OBJECTIVE
Empowering underprivileged people through skill development
Supporting Students/ Youth/Women/Jobless People through Scholarship, Training, Workshop, Consultation
Create Opportunity for
future work-force
IMPLEMENTATION PLAN
Phase1:
Scholarship
Online Session
Event/Workshop
Phase2:
Infra Setup
Hire staff
Diversification
  Education
  Women
  Youth
  Entrepreneur
CHALLENGES & MITIGATION
Challenges:
Securing sustainable funding for long-term operations.
Online Platform and Infra
development
Mitigations:
Ensuring consistent attendance and program
engagement.
Partner with local
organizations to identify people and promote the program.

## Slide 5: PROJECT 3: Bridge Hub/ Talent Connect/Pro-Net/Network-Xcel
OBJECTIVE
Create a platform for networking and collaboration
Building a worldwide network
Connecting aspiring professional/entrepreneur with experienced mentors to provide support, advice, and guidance
IMPLEMENTATION PLAN
Develop the online/offline platform to connect people and Establish team.
Launch a marketing campaign to attract professionals/ entrepreneur.
Conduct workshops, webinars, and one-on-one sessions.
Organize regular networking events and an annual summit.
CHALLENGES & MITIGATION
Challenge:
Ensuring long-term engagement without high costs.
Reaching talent with
limited access.
Mitigation:
Partner with local businesses, NGOs, and focused organizations.

## Slide 6: ANNEXURE

## Slide 7: PROJECT 1: GREEN CITY CLEAN CITY - Budget Details (Phase1 and 2)
Community Engagement and Awareness - Estimated Cost: 30,000 BDT
  Workshops or events to educate local communities about tree care and the project's benefits. May use Printed materials or posters.
Sapling Purchase - Estimated Cost: 300 BDT per sapling, totaling 2,40,000 BDT
  Tree Types: Mango, jackfruit, guava, coconut, etc., suitable for the regions.
  Quantity: ~500 saplings for one model city, ~300 for one model village.
Planting and Maintenance - Estimated Cost: 2,00,000 BDT
  Labor Costs: Hiring local workers for planting and maintenance (watering, soil prep).
  Tree Guards/Fencing: Bamboo made guards; 100 BDT per sapling, totaling 80,000.
  Fertilizers and Organic Manure: for healthy growth; 50 BDT/sapling, totaling 40,000.
Monitoring and Reporting - Estimated Cost: 50,000 BDT
  Regular site visits to ensure saplings thrive.
  Reporting to stakeholders (NRB GROUP).
Contingency Fund - Estimated Cost: 50,000 BDT
  To address unforeseen expenses like pest control/extreme weather/local people manage.
Total Budget: BDT 570,000

## Slide 8: PROJECT 2: Skill Development - Budget Details (Phase 1 and 2)
Infrastructure Setup:
  Facility rental or lease (per year): BDT 300,000
  Renovation and furnishing (training rooms etc.): BDT 200,000
Basic Amenities:
  Food and Utilities (electricity, water, etc., for 20 people/year): BDT 100,000
  Medical care and counseling services: BDT 100,000
  Vocational Training:
    Trainers' fees and training materials: BDT 400,000
    Equipment for skill development (e.g., sewing machines, carpentry tools): BDT 150,000
  Business Support Fund:
    Seed funding for small businesses (20 individuals, BDT 10,000 each): BDT 200,000
    Follow-up support and mentorship: BDT 50,000
  Operational Costs:
    Salaries for staff (coordinator, trainers, caregivers): BDT 400,000
    Communication and outreach: BDT 50,000
  Contingency and Miscellaneous:
    Unforeseen expenses: BDT 50,000
Total Budget: BDT 2,000,000

## Slide 9: PROJECT 3: Networking - Budget Details (Phase 1 and 2)
Platform Development:
  Hosting, maintenance, and updates (first year): BDT 100,000
  Mentorship Program Setup:
    Outreach to organize mentors and participants: BDT 50,000
    Honorariums for mentors: BDT 150,000
    Operational Costs:
      Project team salaries (coordinator, support staff): BDT 250,000
      Utilities and communication: BDT 50,000
    Events and Networking:
      Monthly webinars and meetups: BDT 200,000
      Annual entrepreneurship summit: BDT 300,000
    Marketing and Outreach:
      Social media campaigns and advertising: BDT 100,000
      Printed materials and local promotion: BDT 50,000
    Contingency and Miscellaneous:
      Unforeseen expenses: BDT 50,000
Total Budget: BDT 1,300,000

## Slide 10: Summary
Project | Budget proposed (BDT) | Challenge | Mitigation/ Execution process
GREEN BD CLEAN BD (add waste management plan?) | 570,000 | Reliable local contacts | Central committee Local committees
EMPOWER-U/ FUTURE READY/SKILL UP | 20,00,000 | Expensive, reliable local contact, funding Support staff for online activities Reach general people | Feasibility study? Social business model? Full time regular paid staff Online based- reduce infrastructure cost Engage political team (MOU)
Bridge Hub/ Talent Connect/Pro-Net/Network-Xcel | 13,00,000 | Communication Volunteers- suit skills and interest | Feasibility study? Train a person who needs this support Efforts to educate people on the benefit?

## Slide 11: Teamwork requirements to perform the projects
Open discussion for feedback
Team formation
Project proposal and feasibility study- researcher 1-2 persons
Project implementation team 5-7 members
  Volunteer NRB representative/s
  Volunteer local contact/s
  Paid project manager (Bangladesh), office admin staff etc. (based on project)
Collaboration with other team (individual/ institution)
  Volunteer NRB representative
  Volunteer from other team

## Slide 12: Work procedure plan
Open discussion for feedback
Key stakeholders- NRB committee, local representatives in Bangladesh, third party (if applicable)
Formal project proposal based a feasibility study.
Identify all tasks.
Distribute work loads based on agreement with members.
Project implementation plan with all stakeholders.
Budget, fund raising initiatives.
Project dissemination, delivery reports.
MOU with third party if required.

## Slide 13: How you can contribute?
Open for discussion
Be a part of the committee and take responsible roles.
Help as a volunteer as required.
Has a specific skillset that can be used for project implementation.
Actively circulate the message for fund raising initiative as required.
Idea person- an active reader and give positive feedback towards successful completion of projects, identify challenges and propose mitigations